# Intelligent Scheduling Assistant — Project Management Plan

## 1) Vision & Objectives

Vision: A personal time optimizer that turns tasks and constraints into a feasible, explainable calendar—balancing learning, deadlines, travel, and rest.

Primary objectives

- Generate conflict-free weekly plans that respect existing calendar events and personal constraints.

- Minimize lateness and fragmentation; preserve stability across replans.

- Build user trust via a separate “Planner” calendar, locks, and “why this here?” explanations.

- Scale to automated intake (Gmail/Canvas) and adaptive daily planning.

North-star success metrics (MVP-level)

- On-time completion rate of dated tasks ≥ 90%.

- Average lateness (minutes) → ~0 within two weeks of usage.

- Plan generation time ≤ 10 s for a 7-day horizon with 20–35 items.

- User-initiated edits after plan ↓ 30% by week 3 (stability).

## 2) Scope by MVP

- MVP 1 — Core Intelligent Scheduler (now)

  - Manual tasks + existing calendar ingestion (read-only).

  - CP-SAT scheduling, sleep windows, min block size, limited splits, basic travel buffers.

  - ICS export or write to a separate Planner calendar.

  - Locks (none/soft/hard), one-click replan.

- MVP 2 — Automated Intake

  - Gmail label-scoped parsing; Canvas assignments sync.

  - Human-in-the-loop review queue.

- MVP 3 — Adaptive Daily Planner

  - Daily suggestions, rollover of unfinished tasks, actuals logging, estimate calibration.

- MVP 4 — Two-Way Integrations

  - Optional write-back/sync with Google Calendar (kept separate) + a to-do app (Todoist/Notion).

## 3) Work Breakdown Structure (WBS)

### Core tracks

- Platform & Data

  - Repo, FastAPI service, DB schema, migrations, time-zone handling, seed data.

- Scheduling Engine

  - CP-SAT model (intervals, NoOverlap, due-date penalties, splits, windows).

  - Fallback greedy heuristic; stability penalty; travel pseudo-events.

- Interfaces

  - API endpoints (/tasks, /events, /plan/generate, /plan/ics).

  - Minimal UI (Streamlit or small React app).

  - ICS export; Planner calendar writer (optional flag).

- Quality & Ops

  - CI, tests, property checks, linting, logging, observability (solve time, objective).

- Security & Privacy

  - OAuth (later), scoped permissions, token storage, audit logs (for MVP 2+).

## 4) Timeline & Milestones (2-week sprints)

| Sprint | Dates (2025) | Theme |
| --- | --- | --- |
| 0 | Oct 7–Oct 10 | Bootstrap: repo, CI, DB schema, seed data |
| 1 | Oct 13–Oct 24 | CRUD for Tasks/Events; time-zone; ICS export |
| 2 | Oct 27–Nov 7 | CP-SAT v1: tasks + events + sleep + splits + due penalties |
| 3 | Nov 10–Nov 21 | Planner calendar writer; locks; minimal UI; stability penalty |
| 4 | Nov 24–Dec 5 | Travel buffers; performance; property tests; polish |
| 5 | Dec 8–Dec 19 | MVP 2: Gmail/Canvas intake + review queue |
| (Holiday break) | Dec 22–Jan 2 | Code freeze, docs |
| 6 | Jan 5–Jan 16, 2026 | MVP 3: daily suggestions, rollover, actuals, calibration |
| 7 | Jan 19–Jan 30, 2026 | MVP 4: to-do app sync (one system), change-sync rules |

Milestones

- M1 (Nov 7): Feasible weekly plan, ICS export, no conflicts.

- M2 (Nov 21): Locks, stability penalty, basic UI, Planner calendar write.

- M3 (Dec 5): Travel buffers + test harness; MVP 1 code complete.

- M4 (Dec 19): MVP 2 demo (email/Canvas → review queue → plan).

- M5 (Jan 16): MVP 3 demo (daily suggestions + rollover).

- M6 (Jan 30): MVP 4 demo (one to-do app sync).

## 5) Detailed Deliverables & Acceptance Criteria

### Sprint 0 — Bootstrap

Deliverables: Repo, FastAPI skeleton, SQLAlchemy models, Alembic migration, seed script.
Acceptance: App boots locally; can list/insert Tasks & Events; unit test scaffold in place.

### Sprint 1 — Data & ICS

Deliverables: CRUD APIs; hour/minute TZ-safe utils; /plan/ics export.
Acceptance: Seeded week exports to ICS; imports cleanly into Google Calendar.

### Sprint 2 — CP-SAT v1

Deliverables: CP-SAT model with:

- Optional intervals (≤ 2 splits), NoOverlap, sleep windows as hard events,

- Tardiness variable per task; objective on lateness + splits.
Acceptance: For 10–20 tasks + 10–15 fixed events:

- Solve in ≤ 10 s; no overlap; total scheduled time matches estimates; hard due-date tasks never exceed due time.

### Sprint 3 — Planner Calendar & Locks

Deliverables: “Planner” calendar writer; block locks; minimal UI.
Acceptance: Plan appears on a separate calendar; moving/locking blocks is respected on replan; stability penalty reduces churn; “Generate plan” round-trip from UI.

### Sprint 4 — Travel & QA

Deliverables: Travel pseudo-events; property tests; performance logging; objective tuning.
Acceptance: Cross-location events automatically inject travel buffers; property tests for overlap/duration/due all pass; P95 solve time ≤ 10 s on sample set.

### Sprint 5 — MVP 2 Intake

Deliverables: Gmail label-scoped parser; Canvas assignments; review queue; audit log.
Acceptance: New assignment/email generates a proposed task with parsed title/due date; one-click accept schedules on next plan.

### Sprint 6 — MVP 3 Adaptive Daily

Deliverables: Daily plan view; rollover; actuals logging; category-level calibration.
Acceptance: Skipped blocks auto-reschedule without violating hard due dates; estimates converge (MAPE ↓ after ≥ 10 logs).

### Sprint 7 — MVP 4 Integrations

Deliverables: Sync with a single to-do app; dedupe & change-source rules.
Acceptance: Tasks created in app appear in external tool; status changes sync both ways without duplicates.

## 6) Roles & RACI

| Area | Responsible | Accountable | Consulted | Informed |
| --- | --- | --- | --- | --- |
| Product & priorities | You | You | QA/UX | Beta users |
| Solver modeling | Solver Eng | Tech Lead | Backend | Product |
| Backend/API/DB | Backend Eng | Tech Lead | Solver, Frontend | Product |
| Frontend/UI | Frontend Eng | Tech Lead | Product | Beta users |
| Security/OAuth | Backend Eng | Tech Lead | Legal (later) | Product |
| QA & Release | QA | Tech Lead | All | Stakeholders |

(Solo builder? You wear all hats; keep the RACI to stay disciplined.)

## 7) Dependencies

- OR-Tools (CP-SAT), Python 3.11+

- Calendar: ICS export; optional Google Calendar API (separate Planner calendar)

- MVP 2+: Gmail API (read-only label), Canvas API (Assignments)

- DB: Postgres in prod, SQLite in dev

- CI: GitHub Actions (lint, type check, tests)

## 8) Risk Register & Mitigations

- NP-hard scheduling → slow solves
Mitigate: cap horizon (7–14 days), 15-min ticks, ≤ 2 splits, 10 s timeout, greedy fallback.

- Bad duration estimates
Mitigate: log actuals in MVP 3; apply category correction factors.

- User trust (calendar thrash)
Mitigate: separate Planner calendar, locks, stability penalty, explainers.

- Noisy email parsing
Mitigate: label-scoped read + review queue; explicit allow/deny rules.

- Travel realism
Mitigate: pseudo-events in MVP 1; real distance matrix in Phase 2.

## 9) Quality Plan

- Code quality: black/ruff; mypy on core; conventional commits.

- Tests: unit (solver helpers), property tests (no overlap; duration conservation; due-date guards), API integration tests.

- Perf targets: P95 plan ≤ 10 s; memory < 1 GB on sample.

- Observability: structured logs (solve time, nodes explored if available, objective breakdown), error tracking.

## 10) Security & Privacy

- Store all times in UTC with user TZ metadata.

- MVP 1: no OAuth (manual ICS). MVP 2: least-privilege scopes, encrypted tokens at rest.

- Clear Data Access page + “Disconnect & purge” button.

- Audit logs for ingested items (source, parse, user decision).

## 11) Budget & Effort (pragmatic estimate)

- Solo dev: ~8–10 weeks to MVP 2; ~14–16 weeks to MVP 4 (part-time coursework aware).

- Cloud & APIs (early): <$50/mo (DB + small VM); later scale to $100–200/mo.

## 12) Communication & Cadence

- Daily 10-min standup (solo note works).

- Weekly demo (Fri) + retro (what to stop/start/continue).

- Backlog grooming mid-sprint (Tue).

- Decision log in /docs/ADR-YYYYMMDD-*.md.

## 13) Requirements Traceability (business → model → test)

| Business need | Model element | Test |
| --- | --- | --- |
| Respect fixed events | Hard IntervalVar; AddNoOverlap | No overlaps with fixed intervals |
| Meet due dates | Tardiness var LtL_tLt​; hard due if flagged | Hard due never violated; soft due penalized |
| Limit fragmentation | Max splits; split penalty | splits_t ≤ 2; penalty reduces splits |
| Sleep & rest | Hard “forbidden window” intervals | No block placed in sleep windows |
| Travel feasibility | Pseudo travel blocks | Travel blocks exist when locations differ |
| Stability across replans | Start-deviation penalty; locks | Lower churn between plans; locked blocks unchanged |

## 14) Backlog (top next items)

- Task form with duration/due/priority/category/location.

- Sleep window settings (per day type).

- CP-SAT v1 + greedy fallback.

- Planner calendar write toggle (off by default, ICS on).

- Lock interactions + stability penalty.

- Travel pseudo-events (configurable defaults).

- Review queue (MVP 2).

- Daily suggestions + rollover (MVP 3).

- To-do sync (MVP 4).

## 15) Go/No-Go Gates

- Gate A (MVP 1 readiness, Nov 21): Feasible, readable weekly plan; locks/stability; ICS + optional Planner calendar; property tests green.

- Gate B (MVP 2 readiness, Dec 19): Intake adds real value without noise; privacy page complete.

- Gate C (MVP 3 readiness, Jan 16): Rollover stable; estimates improving week-over-week.

- Gate D (MVP 4 readiness, Jan 30): Sync loop-safe; dedupe proven.

## 16) What you do this week

- Spin up repo & DB (Sprint 0 checklists).

- Implement Tasks/Events CRUD with UTC handling.

- Seed a realistic week (classes, club, 10 tasks) and export ICS.

- Start CP-SAT model scaffold with tests for:

  - NoOverlap holds

  - Sum of task blocks equals estimate

  - Hard due dates never violated

If you want, I can immediately draft the exact FastAPI endpoints, SQLAlchemy models, and a first CP-SAT function signature you can paste in—and a tiny JSON seed you can load to generate your first plan.