## Overview
Zeit Project Management Dashboard
Metric | Value
Total Deliverables | 2500%
Completed Deliverables | 100%
Average Completion | 7%
Open Risks | 500%
Highest Severity | 0%
Sprint | Total Deliverables | Average Completion
0 | 5 | 35%
1 | 3 | 0%
2 | 2 | 0%
3 | 3 | 0%
4 | 3 | 0%
5 | 3 | 0%
6 | 3 | 0%
7 | 3 | 0%

## Timeline & Milestones
Sprint | Start Date | End Date | Theme | Status | Deliverables | Acceptance Met? | Comments
0 | 2025-10-07 | 2025-10-10 | Bootstrap | In Progress | Repo, FastAPI skeleton, SQLAlchemy models, Alembic migration, seed script
1 | 2025-10-13 | 2025-10-24 | CRUD & TZ & Export | Not Started | CRUD for Tasks/Events; time-zone; /plan/ics export
2 | 2025-10-27 | 2025-11-07 | CP-SAT v1 | Not Started | CP-SAT v1: tasks + events + sleep + splits + due penalties
3 | 2025-11-10 | 2025-11-21 | Planner & Locks | Not Started | Planner calendar writer; locks; minimal UI; stability penalty
4 | 2025-11-24 | 2025-12-05 | Travel & QA | Not Started | Travel pseudo-events; performance; property tests; polish
5 | 2025-12-08 | 2025-12-19 | MVP 2 Intake | Not Started | Gmail label-scoped parser; Canvas assignments; review queue; audit log
6 | 2026-01-05 | 2026-01-16 | MVP 3 Adaptive Daily | Not Started | Daily plan view; rollover; actuals logging; category-level calibration
7 | 2026-01-19 | 2026-01-30 | MVP 4 Integrations | Not Started | Sync with a single to-do app; dedupe & change-source rules

## Deliverables
Sprint | Feature | Deliverable | Acceptance Criteria | Owner | Completion | Comments
0 | Bootstrap | Repo setup | App boots locally; can list/insert tasks & events; unit test scaffold in place | Alexandre | 100%
0 | Bootstrap | FastAPI skeleton | App boots locally; can list/insert tasks & events; unit test scaffold in place | Alexandre | 50%
0 | Bootstrap | SQLAlchemy models | App boots locally; can list/insert tasks & events; unit test scaffold in place | Alexandre | 25%
0 | Bootstrap | Alembic migration | App boots locally; can list/insert tasks & events; unit test scaffold in place | Alexandre | 0%
0 | Bootstrap | Seed script | App boots locally; can list/insert tasks & events; unit test scaffold in place | Alexandre | 0%
1 | Data & Export | CRUD APIs | Seeded week exports to .ics; imports cleanly into Google Calendar | Alexandre | 0%
1 | Data & Export | Timezone-safe utils | Seeded week exports to .ics; imports cleanly into Google Calendar | Alexandre | 0%
1 | Data & Export | ICS export | Seeded week exports to .ics; imports cleanly into Google Calendar | Alexandre | 0%
2 | CP-SAT v1 | Interval model | Solve <= 10 sec; no overlap; hard due dates respected | Alexandre | 0%
2 | CP-SAT v1 | Tardiness penalty | Solve <= 10 sec; no overlap; hard due dates respected | Alexandre | 0%
3 | Planner & Locks | Planner calendar writer | Plan appears on separate calendar; locking respected on replan | Alexandre | 0%
3 | Planner & Locks | Lock mechanism | Plan appears on separate calendar; locking respected on replan | Alexandre | 0%
3 | Planner & Locks | Minimal UI | Plan appears on separate calendar; locking respected on replan | Alexandre | 0%
4 | Travel & QA | Travel pseudo-events | Cross-location events automatically inject travel buffers; property tests pass | Alexandre | 0%
4 | Travel & QA | Performance logging | Cross-location events automatically inject travel buffers; property tests pass | Alexandre | 0%
4 | Travel & QA | Objective tuning | Cross-location events automatically inject travel buffers; property tests pass | Alexandre | 0%
5 | MVP 2 Intake | Gmail label parser | New assignment/email generates proposed task with parsed title & due date | Alexandre | 0%
5 | MVP 2 Intake | Canvas assignments | New assignment/email generates proposed task with parsed title & due date | Alexandre | 0%
5 | MVP 2 Intake | Review queue | New assignment/email generates proposed task with parsed title & due date | Alexandre | 0%
6 | MVP 3 Adaptive Daily | Daily plan view | Skipped blocks auto-reschedule; estimates converge after logs | Alexandre | 0%
6 | MVP 3 Adaptive Daily | Rollover mechanism | Skipped blocks auto-reschedule; estimates converge after logs | Alexandre | 0%
6 | MVP 3 Adaptive Daily | Actuals logging | Skipped blocks auto-reschedule; estimates converge after logs | Alexandre | 0%
7 | MVP 4 Integrations | To-do app sync | Tasks sync both ways without duplicates | Alexandre | 0%
7 | MVP 4 Integrations | Dedupe rules | Tasks sync both ways without duplicates | Alexandre | 0%
7 | MVP 4 Integrations | Change-source rules | Tasks sync both ways without duplicates | Alexandre | 0%

## Risk Register
Risk | Probability (1-5) | Impact (1-5) | Severity | Mitigation | Owner | Status
NP-hard scheduling → slow solves | 4 | 5 | 20 | Cap horizon; 15-min ticks; ≤2 splits; 10s timeout; greedy fallback | Alexandre | Open
Bad duration estimates | 3 | 4 | 12 | Log actuals; apply category correction factors | Alexandre | Open
User trust (calendar thrash) | 3 | 4 | 12 | Separate Planner calendar; locks; stability penalty; explainers | Alexandre | Open
Noisy email parsing | 2 | 3 | 6 | Label-scoped read + review queue; explicit allow/deny rules | Alexandre | Open
Travel realism | 2 | 2 | 4 | Pseudo-events in MVP 1; real distance matrix in Phase 2 | Alexandre | Open

## Quality & Performance
Metric | Target | Actual | Variance | Notes
On-time completion rate | 90% |  | -90% | Target 90% of tasks completed by due date
Average lateness (minutes) | 0% |  | 0% | Aim for zero lateness
Plan generation time (s) | 1000% |  | -1000% | Solve within 10 seconds for a 7-day horizon
User-initiated edits after plan (delta %) | -30% |  | 30% | Decrease edits by 30% by week 3
Tests passing rate | 95% |  | -95% | Aim for at least 95% of tests passing

## Backlog & Next Up
Task | Priority | Sprint Target | ETA | Blocked? | Notes
Task form with duration/due/priority/category/location | High | 1 | 2025-10-24 | No | Core data structure
Sleep window settings (per day type) | High | 1 | 2025-10-24 | No | Configure rest periods
CP-SAT v1 + greedy fallback | High | 2 | 2025-11-07 | No | Combine CP-SAT model with fallback
Planner calendar write toggle | Medium | 3 | 2025-11-21 | No | Toggle to enable/disable Planner calendar write
Lock interactions + stability penalty | Medium | 3 | 2025-11-21 | No | Respect locks on replans; add stability penalty
Travel pseudo-events (configurable defaults) | Medium | 4 | 2025-12-05 | No | Pseudo events for travel buffers
Review queue (MVP 2) | Low | 5 | 2025-12-19 | No | List of incoming tasks for human review
Daily suggestions + rollover (MVP 3) | Low | 6 | 2026-01-16 | No | Suggest tasks daily and roll over unfinished ones
To-do sync (MVP 4) | Low | 7 | 2026-01-30 | No | Integrate with external to-do app
Dedupe rules | Low | 7 | 2026-01-30 | No | Rules to deduplicate tasks across systems

## Retro & Decisions
Date | Stop (What to stop) | Start | Continue | Key Decisions | Gate (Go/No-Go)

## Requirements -> Tests
Business Need | Model Element | Test Name | Result (Pass/Fail) | Link to File
Respect fixed events | Hard IntervalVar; AddNoOverlap | No overlaps with fixed intervals
Meet due dates | Tardiness var; Hard due if flagged | Hard due never violated; Soft due penalized
Limit fragmentation | Max splits; split penalty | splits_t ≤ 2; penalty reduces splits
Sleep & rest | Hard forbidden window intervals | No block placed in sleep windows
Travel feasibility | Pseudo travel blocks | Travel blocks exist when locations differ
Stability across replans | Start-deviation penalty; locks | Lower churn between plans; Locked blocks unchanged